## Slide 1: PERMITTING LARGE PROJECTS IN ALASKA
Office of Project Management and Permitting
Department of Natural Resources

## Slide 2
Years
30 35 40 45 50 55 60
0 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15
Initial Exploration
Advanced Exploration
Environmental Studies
Prefeasibility
Study
Feasibility
Study
Permitting
Financing
Construction
Operation
Closure
Post-Closure Monitoring
POTENTIAL TIMELINE FOR MINING PROJECT

## Slide 3: PARALLEL PROCESSES
3
NEPA - EIS
Process
Federal
Process
State
Process
Local
Process
Record of Decision
Federal
Permit, Certification, Approval
State
Permit, Certification, Approval
Notice of Intent
Scoping
Draft EIS
Final EIS
ADFG
Fish Habitat Permit
Monitoring Plan
Army Corps
Wetlands
E.O. 13175
Tribal Consultation
USFWS/NMFS
Endangered Species Act
Consultation
NMFS
Magnuson-Stevens
Fisheries Management Act
Marine Mammal Protection Act
EFH Assessment
ADNR
Land use authorization
Financial Assurance
National Historic Preservation Act
ADEC
Wastewater Discharge (APDES)
Waste Management
Air Quality Permit
401 Certification
Monitoring Plan
City Plan
Borough Plan
Local
Consistency
Analysis
OPMP works to integrate the permitting processes so they run concurrently

## Slide 4
State/Federal Large Project Permitting Agencies
4
STATE DEPARTMENTS
Natural Resources (ADNR)
Transportation & Public Facilities (ADOTPF)
Environmental Conservation (ADEC)
Fish and Game (ADF&G)
Health and Social Services (ADHSS)
FEDERAL
US Army Corps of Engineers
US Environmental Protection Agency
US Fish and Wildlife Service
NOAA-National Marine Fisheries Service
Federal Land Managers: Bureau of Land Management/U.S. Forest Service/U.S. Fish & Wildlife Service/U.S. Park Service
Federal Energy Regulatory Commission
Bureau of Ocean, Energy Management, Regulation and Enforcement
US Coast Guard

## Slide 5: National Environmental Policy Act (NEPA) Process for an EIS
Baseline
Studies
Federal Permit
Applications/
EIS
Notice of Intent
Public Scoping
Alternatives
Development
And
Analysis
Issuance of
Draft EIS &
Draft State
Permits
Public Comment
Evaluation &
Response to
Comments
Issuance of
Final EIS
Public Comment
No Action
Period (30 days)
RECORD OF
DECISION
(ROD)
ISSUANCE OF
PERMITS ?
?
State works to coordinate its permit process with NEPA

## Slide 6
Define Purpose and Need
Proposal
Environmental Assessment (EA)
Categorical Exclusion?
Extraordinary Circumstances
Automatic CE
REC CE
Complete REC
Draft EIS
Public Involvement
Final EIS
Waiting Period
Record of Decision
NOI --Appropriate Scoping
Initial Scoping (environmental analysis)
Appropriate Public Involvement
Scoping (environmental analysis)
FONSI
Make action decision
Implement decision (with mitigation and/or monitoring when specified in the decision)
Significance of Impacts is uncertain EA
Significant Impacts will occur EIS
NO
NO
NO
Impacts Significant
YES
NO

## Slide 7
Office of Project Management and Permitting
Fish & Game
Natural Resources
Health and Social Service
Transportation & Public Facilities
Law
Environmental Conservation
Revenue
Large Mine Permit Team
Alaska Pollution Discharge Elimination System (APDES)
Financial Assurance
Waste Management Permit (WMP)
Fish Habitat Permits
Health Impact Assessment (HIA)
Air Permit
Mining Claim
Application for Permits to Mine in Alaska (APMA)
Plan of Operations (POO)
Reclamation & Closure Plan
Temporary Water Use Authorization (TWUA)
Water Reservations
Dam Safety Certifications
Land Use Permit
Land Lease
Material Site
Public Rights-of-Way
Fish Resource Permits
Heavy Haul Permit
Water Right
Land Easement
National Environmental Policy Act (NEPA) Process
Bureau of Land Management (BLM)
Corps of Engineers (USACE)
Forest Service (USFS)
Environmental Protection Agency (EPA)
Advisory role
Formal authority
Public Notice Required
Key
Material Sale
Camp Permit (individual or general)
Cultural Resource Investigation
Spill Prevention & Response (SPAR) Authorizations
For public information purposes. More information is available at http://dnr.alaska.gov/commis/opmp/

## Slide 8: PROCESSES/PERMITS WITH THE LONGEST LEAD TIME
NEPA
  Development of an Environmental Impact Statement (EIS)
  Baseline data collection
  Inconsistencies in Federal processes and methodologies
Air permits - Prevention of Significant Deterioration Permit (PSD)
  Several years to collect baseline data

## Slide 9
Baseline Studies
9
State recommends early consultation with regulating agencies to help assure correct baseline information is collected.
Surface Water Quality & Quantity
Groundwater Quality & Quantity
Aquatic Life (Includes Marine & Freshwater Fish, Invertebrates, etc.)
Traditional Ecological Knowledge
Health Impact Assessment
Wildlife
Wetlands
Socioeconomics
Subsistence
Cultural Resources
Air Quality
Geotechnical
Visual Resources
Noise

## Slide 10: LITIGATION
Litigious society
Can cause severe time delays
Can potentially make baseline data stale
The fear of litigation can add to timelines and can often lead a process to goes above and beyond what is reasonable
Sometimes litigation can make future decisions or processes more efficient or transparent depending on the situation and outcome

## Slide 11: EARLY COORDINATION
Project proponents should start a dialog with State, Federal, and local entities early in the process
  Reduce timelines and costs by identifying and understanding agency needs & requirements early on in the process allowing applicants to propose a project that considers all of those needs in the early stages of design
  Helps assure that everyone is on the same page about baseline data and collection

## Slide 12: QUESTIONS AND CONTACT
Jeff Bruno
907-269-7476
jeff.bruno@alaska.gov
Office of Project Management &
Permitting (OPMP), Department
of Natural Resources