## Slide 2: Purpose of the Project
Construct surface access (industrial) to the Ambler Mining District
Support exploration and development of mineral resources in the Ambler Mining District

## Slide 3: Where is the Ambler Mining District?

## Slide 4: Resource Rich Region
75 mile long State-owned mineralized area,
Copper, zinc, lead, silver and gold
Key deposits:
  Arctic (Nova Copper)
  Sun (Andover Ventures)
  Bornite (NANA)
  Smucker (Teck Cominco)
Mine feasibility studies show overland transportation is required for mining to be economically feasible

## Slide 5: Project Development To Date
DOT&PF initiated transportation reconnaissance efforts in 2010
  Community outreach/consultation
  Project website, 20+ public meetings, newsletters/emails
Preliminary engineering
  Design criteria, corridor identification/analysis, cost estimating
Preliminary baseline environmental research
  Preliminary wetland/vegetation mapping, baseline biological studies
  Socioeconomic analysis, subsistence study data gap analysis
Other work completed
  Aerial and contour mapping, geotechnical investigations
Identified feasible routes

## Slide 6: Analysis of Preliminary Corridors
Preliminary corridors were evaluated on:
  Corridor length
  Federal Conservation System units (e.g. wildlife refuges)
  Wild and Scenic Rivers
  Salmon/sheefish habitats
  Caribou habitats
  Threatened/endangered species and critical habitats
  Wetland habitats
  Availability of material sites
  Construction/maintenance cost

## Slide 7: Brooks East Corridor
  200+/- miles long
  Four maintenance stations
  15 large bridges (>150 feet)
  Least caribou impacts, no endangered species impacts
  Least impact on salmon/sheefish habitats
  Corridor through Gates of the Arctic National Park & Preserve was reserved in ANILCA
  Generalized Land Status
    120+/- miles on State land
    20-30 miles on federal (NPS/BLM) land
    40+/- miles on ANCSA Corporation lands

## Slide 8
Proposed Corridor and Alternatives

## Slide 9: Community Input on Proposed Access
High level of interest in communities throughout the region
Many of the comments have centered on:
    Subsistence impacts
    Economic issues (employment, cost of living, etc.)
    Access (restricted vs. public) and number of vehicles
    Environmental issues (wilderness, asbestos, acid rock drainage)

## Slide 10: Different than Dalton Highway
Was constructed using a public ROW from BLM and closed by Commissioner of Transportation
Dalton Highway ROW was owned by State and road was managed by DOT&PF – Commissioner had authority to open or close road
Dalton Highway was placed on the Federal Aid Highway System – allowed federal funds to be used for maintenance

## Slide 11: Similar to Red Dog Mine Road
Controlled access – for industrial use only
Road is narrower and lower than public highway
User tolls used to fund/repay construction and maintenance
Lessons learned on Red Dog Mine Road:
  How to deal with caribou crossing road
  Working with local community to identify needed road crossings
  Covered/closed containers to limit potential for dust
  Commercial driver training/enforcement

## Slide 12
Red Dog Mine Road

## Slide 13: Proposed Project Schedule
Community Outreach/Consultation | 2011-2018
Routing/Reconnaissance Studies | 2010-2013
Baseline Environmental | 2012-2015
Preliminary Engineering | 2013-2015
Submit permit app. to initiate EIS Public Private Partnership Development | 2014 2016
Permitting/Final Design | 2016-2018
Construction Start | 2019

## Slide 14: Proposed Tasks FY2015
Environmental documentation/permitting
  EIS coordination
  Continued Agency consultations
Community outreach/meetings
Additional baseline studies
  Additional hydrology studies (UAF, contractor)
  Additional biological studies (ADF&G, contractors)
  Cultural resources and subsistence studies (ADF&G, contractors)
  Additional geotechnical studies (DOT&PF, contractor)
  Additional economic/financial studies
Preliminary engineering
  Support for NEPA review (alignment refinement, alternative alignments)

## Slide 15: FY15 Activities Funding
AGENCY | FY15 | SCOPE OF WORK
Project Mgmt/Legal | $1,250,000 | AIDEA personnel charges, outside legal counsel for NEPA process.
Public Outreach | $700,000 | PI services including local community liaison services.
Third-Party EIS | $1,000,000 | Third-party contractor to work on EIS under lead federal agency direction.
Hydrology Studies | $600,000 | Meteorological data collection, stream gauging on the 4-5 major rivers, snow surveys (snow depth and snow water equivalent), suspended/bedload sediment studies.
Fisheries Studies | $1,200,000 | Fisheries and habitat studies by ADF&G over 2-3 years.
Geotechnical Studies | $1,000,000 | DOT&PF geotechnical drilling and studies to identify material site, quantify material site quantities, and provide geotechnical recommendations.
Health Impact Assessment | $500,000 | DNR OPMP project coordination manager and HIA development. HIA funding assumed to be split btw FY15 and FY16.
Other Enviro/Engineering | $1,250,000 | Cultural resources, other environmental, engineering support for EIS and permitting.
Federal Cost Reimbursement | $1,000,000 | NPS/FHWA cost recovery as allowed under federal law for processing ROW permit application on federal lands.
TOTAL | $8,500,000 | 

## Slide 16: Project Cost to Completion Estimates
Phase | FY15 | FY16 | FY17 | FY18 | FY19 | Total
Pre-Design/Enviro | $8.5 | $8.5 | $7.0 | $6.5 |  | $30.5
35% Design/Permitting |  |  |  | $5 | $5 | $10
Right-of-Way |  |  |  |  | $3.5 | $3.5
Design/Construction (Design/Build) |  |  |  |  | $290-400 | $290-400
Total | $8.5 | $8.5 | $7.0 | $11.5 | $298.5-408.5 | $334-444

## Slide 17: Introduction to Public Private Partnerships (P3)
P3 is a project delivery method
Combines design, build, finance, operate & maintain functions
Allocates different risks to the public & private sectors
US leads the world in power P3 but lags in other sectors
Transportation P3 now gaining momentum in US

## Slide 18: Rationale for P3
Transfer design, construction, O&M risk to private sector
Provide incentives for cost control & proper maintenance
Attract subordinate equity financing

## Slide 19: Spectrum of P3 Options

## Slide 20: Questions/Discussion