


**Tanana River Bridge**

**Quarterly Progress Report**

**January 15, 2013**

****

**This report covers the period:**

**October 1, 2012 through December 31, 2012**

[www.**northernrailextension**.com](http://www.northernrailextension.com)

**Project Summary**

The Northern Rail Extension (NRE) project proposes to construct and operate an approximately 80-mile-long rail extension from Fairbanks to Delta Junction. The NRE project will begin at the existing rail line located on the Eielson Branch line at the Chena Overflow Bridge just south of the community of North Pole and be extended to the community of Delta Junction, with the ability to service Fort Greely.

The project phases are as listed:

* **Phase 1: Bridge, approach road, and levee associated with the crossing of the Tanana River near Salcha. (Current Phase)**
* Phase 2: Approximately 13 miles of rail from Fairbanks to the Tanana River crossing.
* Phase 3: Approximately 30 miles of rail from the west side of the Tanana River crossing to the Tanana Flats Training Area,
* Phase 4: Approximately 38 miles of rail between the Tanana Flats Training Area and Delta Junction.

**Current Status**

Rip Rap deliveries ended in early November. Approximately 250,000 tons have been delivered and placed. 180,000 tons remain for delivery in 2013.

Fourth quarter of 2012 saw completion of Piers 2, 3, 4, 8, 9, 11 and 17. These piers are all wrapped in blankets and plastic for the winter. Piers 16, 15, 7, and 6 are staged for concrete placement and completion in February, March and April prior to break up. Additional piers may be started based on weather conditions at the time. The contractor will fall short of their goal of completing 14 piers prior to break up. However, with the early delivery of the bridge girders the project is still tracking on schedule.

The 165’ girder deliveries from Valdez to the site began in November. 14 of 80 girders have been delivered to the site. 32 are scheduled to be on site by February 1st with the balance expected prior to weight restrictions, around June 1st. The bridge has 20 spans, consisting of 4 girders for each span. Earlier than scheduled delivery of girders will allow the contractor to loft several girder spans prior to break up. This will allow the contractor to build less river access than originally planned for the 2013/2014 construction season



**Next Quarter Outlook**

First quarter of 2013 activities will include:

* Continued girder deliveries to the site from Valdez.
* Balance of girders delivered to Valdez from the fabrication shop.
* Completion of piers 6, 7, 15, and 16 by the end of March.
* Lofting of some girder spans onto completed piers.

**Safety**

7

**Incidents this Quarter**

90

**Injury Free Days**

10

**Total incidents to date**

**Alaska Work Force (this quarter)**

123

**Total Manpower on Site**

86

**Alaskan Manpower on Site**

70% Alaskans employed on-site this Quarter

**Alaskan Companies providing services:**

**Construction**

* **Rolling Stone Construction:** Gravel Salcha
* **Alaska Quality Insulators:** Office Set upNorth Pole
* **Brice Inc:** Rip RapFairbanks
* **Alaska Industrial:** Trucking Fairbanks
* **Northstar Terminal and Stevedore:** Crane Valdez
* **Brown’s Hill Quarry**, Rip Rap North Pole
* **JD Steel:** Ironwork-Rebar Salcha
* **HC Redimix:** Concrete North Pole
* **Code 3 Logistics:** On-Site Trucking North Pole
* **Bighorn Enterprises:** Trucking Fairbanks
* **Arctic Surveys Company:** Survey Fairbanks
* **Warwick Surveying:** Survey Anchorage
* **Carlile:** TruckingAnchorage

**Engineering**

* **HDR Alaska:** Contract Management/Engineering Anchorage
* **Hanson Alaska:** Bridge Engineering Anchorage
* **Shannon and Wilson:** Geotechnical Engineering Fairbanks
* **PDC Inc:** Survey Fairbanks
* **MAPPA** Testing ServicesFairbanks

**Public Outreach**

* On site open House held December 8th for the local community. Holiday turkeys were distributed. Principal of Salcha elementary provided a presentation of the school’s participation in the project required Pile Driver Slough monitoring experience.

**Funding**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Spent FRA** | **Remaining FRA** | **Spent State Funds** | **Remaining State Funds** | Total |
| **Engineering, Design, Permitting** | $ 13,547,597 | $ - | $ 821,562 | $ 3,130,841 | $ 17,500,000 |
| **Right-of-Way** | $ 635,384 | $ - | $ 213,361 | $ - | $ 848,745 |
| **Construction Administration** | $ 3,671,425 | $ - | $ 2,605,670 | $ 4,987,521 | $ 11,264,616 |
| **ARRC Contingency** | $ - | $ - | $ - | $ 5,061,813 | $ 5,061,813 |
| **Construction Contract** | $ 52,373,840 | $ 33,971,754 | $ 1,424,435 | $ 65,754,797 | $ 153,524,826 |
| **Total** | **$ 70,228,246** | **$ 33,971,754** | **$ 3,911,477** | **$ 78,934,972** | **$ 188,200,000** |

**Schedule**

August 2014

**Original Estimated Schedule completion Date:**

August 2014

**Current Estimated Schedule completion Date**

**Project Milestones**

|  |  |  |
| --- | --- | --- |
| **Major Project Milestones** | | |
|  | **Date** | **Status** |
| **Final Design and Permits** | **July-11** | **Complete** |
| **Construction Contract** | **July-11** | **Complete** |
| **Office Complex & Staging Area** | **November-11** | **Complete** |
| **Utility Relocation** | **November-11** | **Complete** |
| **North Bank Levee** | **July-12** | **Complete** |
| South Bank Spur Dikes | September-13 |  |
| Bridge Sub-Structure | March-14 |  |
| Bridge Super-Structure | March-14 |  |

**ARRC Project Staff**

**On-Site Project Manager**

Mark Peterburs– Project Director

Salcha Project Office – 677-4731

748-1767 or 378-1762 (cell numbers)

[peterbursm@akrr.com](mailto:peterbursm@akrr.com)

**Anchorage Staff**

Tom Brooks – ARRC Chief Engineer

327 West Ship Creek Avenue

Anchorage, AK 99501

907-265-2595

[brookst@akrr.com](mailto:brookst@akrr.com)

Clark Hopp – Director Special Projects

327 West Ship Creek Avenue

Anchorage, AK 99501

907-265-2372

[hoppc@akrr.com](mailto:hoppc@akrr.com)

[www.**northernrailextension**.com](http://www.northernrailextension.com)